## Phase 1 Tickets
Echo — Phase 1 Build Tickets
30 tickets across 5 build phases · Owners: Harshith, Shreya
Step | Task | Type | Owner | Priority | Estimate | Depends On | Status | Phase | Est (days, numeric)
1 | Set up repo - create frontend and backend folders | Setup | Harshith | P0 | 0.5d |  | To Do | Foundation | 0.5
2 | Set up basic backend server (FastAPI) - hello world running locally | Backend | Harshith | P0 | 0.5d | Step 3 | To Do | Foundation | 0.5
3 | Set up basic frontend app (Next.js/React) - hello world running locally | Frontend | Shreya | P0 | 0.5d | Step 2 | To Do | Foundation | 0.5
4 | Connect frontend to backend - basic API call working end to end | Frontend | Shreya | P0 | 0.5d |  | To Do | Foundation | 0.5
5 | Set up Postgres database locally | Backend | Harshith | P0 | 0.5d | Step 6 | To Do | Foundation | 0.5
6 | Set up MinIO (local storage for audio files) | Backend | Harshith | P0 | 0.5d | Step 5 | To Do | Foundation | 0.5
7 | Build person profile - backend API (save/fetch person) | Backend | Harshith | P0 | 0.5d |  | To Do | Foundation | 0.5
8 | Build person profile - create/view screen (no login) | Frontend | Shreya | P0 | 0.5d |  | To Do | Foundation | 0.5
9 | Build audio recording screen - record and play back audio in browser | Frontend | Shreya | P0 | 1d | Step 10 | To Do | Voice Engine | 1
10 | Build audio upload API - save recording to MinIO + Postgres | Backend | Harshith | P0 | 1d | Step 9 | To Do | Voice Engine | 1
11 | Research open-source voice cloning models - shortlist 2-3 (XTTS-v2, F5-TTS, OpenVoice) | Research | Both | P0 | 1d |  | To Do | Voice Engine | 1
12 | Install shortlisted models on M1 Pro laptops - confirm they run | Research | Harshith | P0 | 1d |  | To Do | Voice Engine | 1
13 | Build a "clone voice" backend endpoint - takes uploaded audio, runs it through a model | Backend | Harshith | P0 | 1.5d | Step 14 | To Do | Voice Engine | 1.5
14 | Build a "generate speech" screen on frontend - type text, hit generate, play result | Frontend | Shreya | P0 | 1d | Step 13 | To Do | Voice Engine | 1
15 | Test each shortlisted model through the app and compare quality | Testing | Both | P0 | 1d |  | To Do | Voice Engine | 1
16 | Pick the best model - go/no-go decision on voice quality | Research | Both | P0 | 0.5d |  | To Do | Voice Engine | 0.5
17 | Design phonetic capture script (~20-40 sentences for cleaner voice samples) | Research | Shreya | P1 | 1d | Step 19 | To Do | Voice Quality Pipeline | 1
18 | Update recording screen to guide user through script sentences + freeform sample | Frontend | Shreya | P1 | 1d |  | To Do | Voice Quality Pipeline | 1
19 | Build audio cleanup pipeline - quality check, noise reduction, segmenting | Backend | Harshith | P1 | 1.5d | Step 17 | To Do | Voice Quality Pipeline | 1.5
20 | Wire cleanup pipeline into upload flow (upload -> clean -> ready for cloning) | Backend | Harshith | P1 | 0.5d |  | To Do | Voice Quality Pipeline | 0.5
21 | Wrap chosen model into a proper voice engine service (swappable, not a script) | Backend | Harshith | P0 | 1.5d |  | To Do | Voice Quality Pipeline | 1.5
22 | Test full flow end to end - profile to capture to clean to clone to playback | Testing | Both | P0 | 1d |  | To Do | Integration & Testing | 1
23 | Fix bugs found during testing | Testing | Both | P0 | 1.5d |  | To Do | Integration & Testing | 1.5
24 | Set up GitHub Actions CI - lint, tests, build checks on PR | DevOps | Harshith | P1 | 1d | Step 27 | To Do | DevOps & Deployment | 1
25 | Set up staging server (self-hosted/free-tier) + deploy via GitHub Actions | DevOps | Harshith | P1 | 1d |  | To Do | DevOps & Deployment | 1
26 | Set up production server + gated deploy via GitHub Actions | DevOps | Harshith | P1 | 1d |  | To Do | DevOps & Deployment | 1
27 | Set up monitoring/logging (Grafana + GlitchTip) on staging and prod | DevOps | Shreya | P1 | 1d | Step 24 | To Do | DevOps & Deployment | 1
28 | Deploy app to staging and test full flow there | Testing | Both | P0 | 0.5d |  | To Do | DevOps & Deployment | 0.5
29 | Check latency - time taken for cloning and playback, log to monitoring | Testing | Both | P1 | 0.5d |  | To Do | DevOps & Deployment | 0.5
30 | Deploy to production | DevOps | Harshith | P0 | 0.5d |  | To Do | DevOps & Deployment | 0.5
Total tickets | 30
P0 tickets | 21
P1 tickets | 9
Total estimated days | 25.5